## Slide 1
Milestone 1: Survey Design and Requirement Definition
25.10.23 Kick-Off
Meeting Check-In – 08.11.23
Participants
David
Ben
Aylin
Chandimal
Jabora
Beyda
Tasks Due
Timeline
„Done“
Milestone 2: Survey Plattform
08.11.23 today
Milestone 3: Experiment
Milestone 4: Data Analysis
1-2 Weeks
2-3 Weeks
1 Weeks
2-3 Weeks

## Slide 2
Milestone 1: Survey Design and Requirement Definition
25.10.23 Kick-Off
Meeting Check-In – 15.11.23
Participants
David
Ben
Aylin
Chandimal
Jabora
Beyda
Tasks Due
Mockup
Versuchsportal
Add more Milestones
„Done“
Milestone 2: Survey Plattform
08.11.23 Coordination
Milestone 3: Experiment
Milestone 4: Data Analysis
1-2 Weeks
2-3 Weeks
2
Week
2-3 Weeks
01.11.23 Team building
15.11.23 Mockup
Milestone 5: Report
2-3 Weeks
Vacation
Lecture Free Time

## Slide 3
Milestone 1: Survey Design and Requirement Definition
25.10.23 Kick-Off
Meeting Check-In – 22.11.23
Participants
David
Ben
Aylin
Chandimal
Jabora
Beyda
Tasks Due
Ethics Form
MS: Survey Design and Requirement Definition
„Done“
Milestone 2: Survey Plattform
08.11.23 Coordination
Milestone 3: Experiment
Milestone 4: Data Analysis
1-2 Weeks
2-3 Weeks
2
Week
2-3 Weeks
01.11.23 Team building
15.11.23 Mockup
Milestone 5: Report
2-3 Weeks
Vacation
Lecture Free Time
22.11.23 today